## Slide 1
S.D. Highway 1889
Weekly Update
8/12/2026
Weekly Meeting:
Weekly Meetings to be held at AGC Building at 300 E Capitol Ave, Suite 1. Enter through side door on S. Highland Street.
Time: 11:00 AM
Day: Wednesdays
Facebook Live Stream: KCCR Radio
KCCR and DRG will keep you up to date with any traffic changes and progress of the project!

## Slide 2
Two-way traffic remains on the southbound lanes from Elizabeth Street to 4th Street
Crossover in place to move two-way traffic to the northbound lane to 4th Street
Curb and gutter installed through 4th Street on the east side
The week of August 17 will start asphalt paving from Elizabeth Street north in the northbound lanes
Will work with business’s where the new asphalt will cross approaches: Delta Dental, Cowboy Country Store and State Motel
Weather dependent, will open 4th Street from Euclid Avenue to Governors Drive in the next two weeks
  4th Street from N Grand Avenue to Euclid Avenue will then close
Wednesday Aug. 12, 2026

## Slide 3
(Weather Dependent) The week of Aug 17 will begin asphalt paving northbound lanes from Elizabeth Street north.
Will coordinate with businesses as new asphalt paving crosses their accesses.

## Slide 4
Pedestrian route crossings of Euclid Avenueto be either at 4th or 5th Street to accommodate construction activities.
Construction Area/Road Closed

## Slide 5
West side of Euclid Avenue and 4th Street is open
Look to open east leg in two weeks (pending weather)
New signal base and concrete curb installed
New signal base and concrete curb installed

## Slide 6
Alternating street closures
Surface removals complete
Water line installation complete
Starting pipe placement
Grading and gravel installation underway

## Slide 7
Crossover will remain in effect until the end of the project

## Slide 8
Expect alternating entrances to business and side streets
(Weather dependent) The east leg of 4th Street will open in the next two weeks between Euclid Avenue and Governors Drive. 4th Street will then close from Euclid Avenue to N Grand Avenue.
Asphalt placement in the northbound lanes from Elizabeth Street north beginning the week of August 17.
Work continues behind the curbs south of Elizabeth Street.
Notices will be sent to the schools regarding crosswalk usage at 4th and 5th Street intersections with Euclid Avenue.
Slow down through work area, be mindful of construction equipment & workers, in addition to kids crossing before and after school.

## Slide 9
Text Notifications:
For updates on major traffic changes during the project, subscribe to a free text-in service. To subscribe, text “EUCLID" to 605-566-4041. Subscribers can unsubscribe at any time.